Graduate School of Development Studies

# EVALUATION OF LIVELIHOODS IN BARANI (RAIN FED) AREAS PROJECT (SLBAP), PUNJAB, PAKISTAN- EXPLORING THE GAPS IN PARTICIPATORY GOVERNANCE AND PROJECT APPROACH

# A Research Paper presented by

Syed Tahir Raza

Pakistan

In partial fulfillment of the requirements for obtaining the degree of

Master of Arts in Development Studies

Specialization

Local and Regional Development

(LRD)

Members of the Examining Committee

Supervisor	            JOAO GUIMARAES

Second Reader	  ERHARD BERNER

The Hague, The Netherlands

September, 2009

TABLE OF CONTENTS

Page

List of Tables.............................................................................................................................4

List of Abbreviations.................................................................................................................5

CHAPTER ONE: GENERAL INTRODUCTION..................................................................  7

1.0	Introduction…………………………………………………………………………..  7

1.1	Background....................................................................................................................8

1.2	Research Objectives…………………………………………………………………. 10

1.3	Justification of the study...............................................................................................12

1.4	Methodology………………………………………………………………………….13

1.4.1	Field Instruments……………………………………………………………………..14

1.5	Scope and Limitations of the study…………………………………………………..15

1.6	Organization of the Research…………………………………………………………16

CHAPTER TWO: CONCEPTUAL FRAMEWORK………………………………………....17

2.1	Introduction……………………………………………………………………...……17

2.1.1	Community………........................................................................................................17

2.1.2	Community Development……………………………………………………………. 18

2.1.3	Community Participation...............................................................................................19

2.1.4	Participatory Governance……………………………………………………………...22

2.1.5	Decentralization, Development and Poverty Reduction………………………………25

2.1.6	Devolution of Power…………………………………………………………………..26

2.2	Analytical Framework……………………………………………...………………....28

2.2.1	Political Party Constellations……………………………………………………….....29

2.2.3	Local Government Institutional set up………………………………………………...29

CHAPTER THREE: SOCIO-ECONOMIC PROFILE OF PROJECT DISTRICTS…………..33

3.0	Introduction……………………………………………………………………………33

3.1.1	Access to Land…………………………………………………………………………34

3.1.2	Poverty in Barani Areas……….……………………………………………………….35

3.1.3	Gender Role…………………………………………………………………………….37

CHAPTER FOUR: EVALUATING PARTICIPATION AND ASSESSING PROJECT ACHIEVEMENTS FOR POVERTY REDUCTION...........................................................…..39

4.0	Introduction……………………………………………………………………………..39

4.1	Peoples Perception of Devolution....................................................................................40

4.2	Local Government and CP………………………………………………………….......41

4.3	UCDC Implementation Mechanism…………………………………………………….42

4.4	Implementation Progress of SLBAP………………………………………………........45

4.4.1	Financial Progress…………………………………………………………………........46

CHAPTER FIVE: FINDINGS AND CONCLUSIONS………………………………………..49

5.0	Introduction ……………………………………………………………………………49

5.1	The Evidence- Case Study of Khushab..........................................................................50

5.2	Ideas & Possibilities-Peoples Perception on Collective Action.....................................52

5.3	Political Leadership........................................................................................................53

5.4	Access to Information…………………………………………………………………54

5.5	Lack of Accountability Mechanism in DGs…………………………………………..55

5.6	Administrative and Financial support…………………………………………………56

5.7	Political Constellations in community based development…………………………...57

5.8	Synthesizing best practices of PG……………………………………………………..57

5.9	Conclusions……………………………………………………………………………58

6	References………………………………………………………………..60

7	Appendices………………………………………………………………..62

LIST OF TABLES

Table 1	 Name of Districts, Tehsils (Sub District) and Number of UCs………………….8

Table 2: 	SLBAP sample Districts, Tehsils, Union Councils, Villages and sample size…37

Table 3: 	Agriculture and Non Agriculture HH in the Project and Non 					Project Area……………………………………………………………………...38

Table 4: 	Classification Of Population By Poverty Status (Poverty Line Rs 1023 Per 			Month)……………………………………………………………………………40

Table 5: 	Head Count Ratios- % of Population Poor by Zone and Project and Control 			Areas……………………………………………………………………………..40

Table 6: 	Devolution And People Perception (Basic Amenities) In The Project, Non   			Project And Overall Areas In Barani Punjab (%Age)…………………………...44

Table 7:	 Cumulative Status of Medium Scale Interventions (MSIs) from 2006-09             			as of June, 2009…………………………………………………………………..49

Table 8: 	Status of Medium Scale Interventions (MSIs) during this Quarter……………...50

Table 9: 	Ranking of Districts as of June 2009…………………………………………….50

Table 10: 	Financial Progress………………………………………………………………..51

Table 11: 	Overall Utilization against Total Allocation……………………………………..51

Table 12: 	Development Fund Utilization in Khushab (Rs in million)……………………...53

Table 13: 	CCB District fund Utilization and SLBAP fund utilization (Rs in million)…….53

Table 14: 	Rural-Urban perceptions on CA/CP in Development (HH survey)……………..55

Table 15:	 Rural-Urban perceptions on leadership in Development (HH survey)…………56

Table 16: 	composite index of significant differences in information sharing (HH 				survey)……………………………………………………………………………57

Table 17: 	Survey of administrative and Financial support to SLBAP from LGs…………..59

LIST OF ABBREVIATIONS

ADB			Asian Development Bank

ADP			Annual Development Programme

APM			Assistant Project Manager

CA			Collective Action

CBO			Community Based Organization

CCB			Citizen Community Board

CD			Community Development

CM			Community Management

CO			Community Organizations

CP			Community Participation

CDP			Community Development Programme

DCO			District Coordination Officer

DG			District Government

DPM			District Project Managers

EG 			Enabling Government

GoP			Government of the Punjab, Pakistan

ISSAS			Institute of Social Studies Advisory Service

LG			Local Government

MoU			Memorandum of Understanding

MSI			Medium Scale Intervention

PG			Participatory Governance

PMU			Project Management Unit

SLBAP		Sustainable Livelihoods in Barani Areas Project

TPA			Targeted Poverty Alleviation

UNDP			United Nation Development Programme

UNCHS		United Nation Centre for Human Settlement

WB			World Bank

CHAPTER ONE: GENERAL INTRODUCTION

- Introduction

In the development field, organizations are constantly seeking best and most effective ways of ensuring poverty reduction around the world. The concept of engaging and involving local communities in the process is not new as well. Popularly known as participation, community participation (CP) has got its conceptual validity in development practice as an effective way where by local people are actively involved in the process and efforts which strive to reduce poverty and raise the economic condition of the poor communities by utilising resources like skills and capacities of the local people. The United Nations (UN), Non Government Organization (NGOs) and Local Governments (LG) have made concerted efforts to ensure community participation in demand driven initiatives for helping the people help themselves. Local Government reforms, commonly known as devolution of power at the local level are the latest initiative of the World Bank currently being experimented in 63 countries around the world.

The main objective of this research is to critically evaluate the extent to which participatory practices in development are effective in poverty reduction by looking at a project titled “Sustainable Livelihood in Barani Areas of Punjab (SLBAP)” As a compliment to the established usefulness of CP as well as to assess the demonstrated ability of the built in provisions of engaging the communities in development, as it is in the local government reforms, this research takes a deep look at this  Asian Development Bank (ADB) initiative currently underway in Pakistan. It is a participatory development programme which relies heavily on the active involvement and input from the institutional set up of the LGs. The efficacy of participation and community engagement is undeniable and therefore widely

practiced in the development world. However the intended results and benefits of participation when put to test have often been surprisingly disappointing and negative and unsuccessful in achieving the intended results

Research will explore the gaps by analyzing the project approach as envisaged and as it turned out to be, by comparative data analysis of the ten (10) project districts through the study of institutional arrangements made for this purpose in the project design and assessing the defined roles of various actors LG, CBOs and NGOs.

1.1 Background

The Sustainable Livelihoods in Barani Area Project (SLBAP) project was started in 2005 after it was decided by the Government of Punjab (GoP), Pakistan to invest for the reduction of poverty in the rain fed areas of the province. As there was already an effort going on for fighting and mitigating the adverse effects of drought in the province for the last ten (10) years and government was spending funds through various programmes and initiatives aided by international donors, the ADB project approach of improved livelihood opportunities and improved governance, proposed for SLBAP was approved by the government of Pakistan as an effort which would yield better results particularly in the backdrop of devolution and decentralization reforms. The institutional system of local governments (LGs) was designed as the engine which would drive the implementation strategy of the intervention. The SLBAP project has been designed for a period of six years and would be completed in 2011. It is sponsored / funded by ADB along with the share of the National Government as well as the beneficiaries. The total outlay of the project is $ 58.6 (m) out of which $ 41 (m) is the share of

ADB funding and $ 8(m) & $ 9(m) is contribution of National Government and the beneficiaries, respectively.

The project is underway in ten (10) predominantly Barani (rain fed area) Districts, spread in 18 Tehsils and 206 Union Councils. The benchmark set for selection of a particular Union Council (UC) is its cultivatable areas more than 75% dependent on rain.

Table 1:  Name of Districts, Tehsils (Sub District) and Number of UCs

| Sr. No. | District | Name of Tehsil | Number of Barani UCs |
| --- | --- | --- | --- |
|  | Rawalpindi | Kotli Sattian | 9 |
|  | Jhelum | Jhelum including Dina | 18 |
|  | Chakwal | Choa Saidan Shah | 7 |
|  | Gujrat | Sarai Alamgir | 7 |
|  |  | Kharian | 28 |
|  | Sialkot | Pasrur | 23 |
|  | Narowal | Narowal | 29 |
|  | Khushab | Khushab | 19 |
|  |  | Noorpur | 10 |
|  | Mianwali | Mianwali | 12 |
|  |  | Isakhel | 13 |
|  | Bhakar | Bhakkar | 9 |
|  |  | Darya Khan | 1 |
|  |  | Kalurkot | 2 |
|  |  | Mankera | 6 |
|  | Layyah | Layyah | 6 |
|  |  | Choubara | 5 |
|  |  | Karor | 2 |
| Total | 10 | 18 | 206 |

In dry land areas of Pakistan, rainfall is the main source of water for raising crops. In these areas the problem in fact is not so much of dependence on rain water, but it is the variability in rainfall from year to year and season to season which has made the farming community more vulnerable. Coupled with this is the fact that southwest Asia and particularly Pakistan is a typical drought affected region having continuous multiple adverse effects. Pakistan has had several drought experiences in the past, recorded as early as in 1899. But the worst and longest spell hit in 1999 and went on till 2002 causing water shortage for crops up to 50% (Shahid A, 2004), resulting in low yields and decreased income for the farmers.

As laid down in SLBAP policy paper specific/immediate objectives are:

- To improve socioeconomic status of poor population through better natural resources management through improved productive, physical, and social infrastructure identified by the elected UCs members and the civil society;

- To reduce poverty of the marginal and poor population through targeted community based initiatives and support to off-farm income generation activities

- To improve the literacy and level of skills through vocational training, specially to the unemployed especially women

- To strengthen the capacity and capability of Project management, and line agencies to implement and support UCs, civil society, and communities in the development process.

As the Project is designed with a process approach, the Project will provide support to beneficiaries according to the prioritized felt need and demand driven interventions. Hence, no quantifiable targets have been fixed.

1.2 Research Objectives

- General Objectives

The overall objective of this research is to study the development project SLBAP in Pakistan to see how it attempts to involve the local government institutional mechanism in achieving the project objectives of poverty reduction by providing livelihood opportunities to the poor communities. As per the implementation design of LG system, the project aims to ensure sustainable empowerment and enablement by creating sustained spaces for maneuvering or the embedded feature of participation has been politicized in the decentralized LG system.

The second research objective is to study the role of various actors as envisaged in the design of the project and what it actually turned out to be and what explains the differences in the interplay and attitudes of various actors.

The LG institutions, despite the embedded mechanism of community participation and citizen involvement in the local economic development, seem to have been behaving contrary to the manner as designed. The very notion of empowerment seems to be serving no purpose for the poor local communities as envisioned in the project and also facilitated in the local government system for citizens empowerment to play a role in development practice.

Citizen Participation (CP) and Community Management (CM) concepts, when put to practice in the local government system, have faced apparent problem owing to the fact that the institutional change being brought about with this concept has not been thoroughly studied. Such a role requires a shift in the behaviors of not only the communities themselves but also the local leaders need to change the traditional lethargic and passive attitude. A major problem for research as well as for practice is that although the concepts of participation have been proven to be instrumental for local economic development, there is little documented evidence on the institutional change at the community and local level in any of the institutions or levels involved in the process. The UNHCS/ISSAS evaluation reports by wils and Helmsing (1998) on practical effectiveness of CP/CM in 7 seven developing countries, where the organizations having undertaken community development programmes involving the target communities have shown good results, yet the effectiveness of community role mechanism of the LG system has yet to prove its sustainability. Gaps like lack of studies about political choice, discrimination, favoritism and inherent community characteristics as well as access issues related to space for citizen participation being occupied, negotiated, subverted or mediated raise a number of questions about the concepts.

- Specific Research Objectives

- To identify and evaluate LG leadership capacity, its capacity to make important decisions, administrative, financial and planning measures, its capacity to engage communities in local development through enacted and recognized rules and procedures and its efficiency, efficacy, transparency and sustainability of actions.

- To recommend improvements in the policy and implementation procedures of the project SLBAP as well as LG.

- To recommend improvements in the crucial LG capacities in future programmes.

1.3 Justifications of the Study

The research is aimed at exploring and evaluating the extent to which the newly established local governments are able to acknowledge and implement the enabled participatory governance concept in the context of the SLBAP project. In this context it is important to recognize that these structures and processes of decision making of the new LG system differ from the previous set of public governance. In the top down governance, government structures at local level were composed by CG. The very essence of decentralization of government at the local level & making an enabling space for maneuvering by multi actors is perceived to be the notion that the top-down models of development planning and implementation, controlled at the level of central governments or provincial governments, did not take local considerations and choices into account nor these models provided any formalized and enabled spaces

forcommunity participation at any level from identification to implementation. It is because of the establishment of new LGs that a new participatory process of decision making that the study is

aimed at finding out if the LGs are ready to assume their new roles and have a positive impact on the lives of the local communities.

SLBAP is one of the various funding initiatives of the Central Governments (CG), World Bank (WB) and various other donors which are aimed at supporting LG and decentralization reforms to promote good governance. SLBAP has been an instrumental project promoting community/citizen participation and improving the technical capacity of local communities and officials in democratic management of resources and services in the LGs of the project districts.

Main aspect of the study is analysis of politicization of the powers, responsibilities and functions at the local level and to explain as to how effective / ineffective was the role of local governments compared to what it has been and what explains the difference in results expected and actually as they are.

1.4 Methodology

This research has used both qualitative and quantitative methods. Quantitative methods are used to explain the observations more clearly and to aggregate, compare and summarize data. A survey questionnaire was used to get information from the LG and CBOs / NGOs in context of community development initiatives of SLBAP project assisted by LG institutional set up as well as to assess the capacity of LG to perform the functions of community engagement. With regard to qualitative data, the research instruments used in this study were bibliographic and secondary data research, semi- structured interviews and observations. The design of these instruments was in accordance with the study’s analytical framework. Furthermore, it was aim of this study to use a multi prong approach of data collection in order to enrich the study, make it more comprehensive and increase its validity.

1.4.1 Field Instruments

Bibliographic Research: This instrument of data collection was useful in finding concepts and theories that construct the study’s analytical framework and its literature review. This framework illustrates the essential capacities that enable LGs to perform their new role effectively (please see analytical framework)

Secondary Data/ Documents: Such as the new LG act and the various by laws which complement it, including the legal and institutional framework for participation and community enablement, was assessed with the aim of finding out about:

- LG new formal roles (functions and responsibilities) in decision making, planning, management and policy implementation, and use of partnerships;

- LG new administrative and financial management working rules and procedures;

- Documents about capacity building programmes delivered to the LGs under study; and

- For the dependent variable-Participation and actual community enablement, research studied LG reports and project documents.

Questionnaire: It was an important source of information for sub questions and thus for the main question of the study. There were two survey questionnaires with specific questions for LG officials and for the engaged CBOs/NGOs. These were relevant in assessing the extent of effectiveness of all actors engaged in community participation in SLBAP project. Also to assess LG capacity to make decisions, plans, manage and implement policies and use partnerships.

Semi Structured Interviews: Semi structured interview were conducted to the Nazim of LGs, members of assembly, field officials and CBO members involved in partnership with the aim to gather as much information as possible. Most of the questions in questionnaire were asked during interviews with these informants to compare their input with the information from questionnaire and documents assessed. The study also purposively selected a number of HHs and LG partners involved.

Ethnographic Observation: This method was applied with the aim of observing relationships among the various actors in LGs under study. A number of LG official meetings and meetings of CBOs were attended to witness CBOs, NGOs and Private Sector involvement in partnership efforts and instances.

1.5 Scope and Limitation of the Study

The research used responses from socio-economic, political and cultural as well as reactions and comments of ADB (Donors) and SLBAP officials. Community responses have been collected from both project and non project areas. This has been done in order to test the validity of different concepts and their outcomes which strive to achieve community development (CD). As the concepts of CP and CM are closely related to the decentralization reform agenda of participation and governance and the project approach and framework also provides implementation mechanism with role of the LGs central in the initiative, this research deals primarily with the governance aspect in participation and community enablement for ensuring sustainable local economic development. One limitation of the research has been its heavily reliance on responses from the community and political leaders as well as other stakeholders which was quantitative data in the shape of questionnaires, interviews and observation, besides a comparative study of the secondary data collected from the project area offices of the LGs, non project districts of the province, NGOs and Project Management Unit (PMU) of the SLBAP project. However, it could not be made possible to collect data from all the 35 provinces which could have served the qualitative aspect of the research.

1.6 Organization of the research

The research paper is divided into five chapters. Chapter two provides theoretical base for concepts used and which are made the basis for investigating and looking into the causalities of various variables related to the research area under investigation. The analytical framework described in chapter two covers the methodology for using indicators for the assessment of community participation and participatory governance mechanism and methodology used in the project. Chapter three covers the socio economic profile of project district. For this description, data from a detailed baseline survey, carried out by SLBAP, has been consulted extensively. The empirical results of surveys and interviews of selected districts and the outcome of secondary data analysis are discussed in chapter three. Chapter four describes the SLBAP project design, planning and implementation mechanisms and later reviews results of empirical data analysis against tested concepts and theories related with research objectives. The last chapter five synthesizes the generated evidence from the research with the theory for describing the best practices in the project area communities. It also attempts to argue and answer certain research questions on the basis of theoretical and data analysis of project area.

CHAPTER TWO: CONCEPTUAL FRAMEWORK

2.1Introduction

According to Peterse and Simone (1994:115), “Development is perhaps more about critically reassessing our own ways of understanding and looking at communities and getting a more in-depth and thorough understanding of what makes communities tick and survive, often in face of impossible odds”. In the society there are also other tiers and invisible factors concerning development which are usually informal layers of the social system making similar efforts while exercising influence on communities. In this way, communities, groups with common interest and household determine what is just, viable and effective for the individual and collective survival of the stakeholders as well as the communities. Once the interplay of interested stakeholders and their choices and preferences become clear, it is a easier to understand the rapport between community development and governance, which then goes on to serve as an understanding about the hypothetical notion of community development and local economic development with the active help and role playing by the communities duly assisted and provided in the institutional mechanisms of the decentralized system of government around the world particularly in the LDCs who are experimenting the LG reforms since 1990s.

2.1.1The Community

A simpler definition and understanding of community is that it involves people living together having common interest and objective. According to Smith (2000) the notion of community is always something of a myth. Commonality of purpose is central to the concept with a visibly distinct identity. “The reality is that communities, more often than not, are made up of an agglomeration of factions and interest groups often locked in competitive relationships”

(Smith, 1990:1). According to Moser, the term ‘Community” has been conceptualized as a homogeneous entity which assumes that everyone is empowered without further clarifying the spatial or social group local power structures (Moser: 1986:306). She further argues that in the conceptualization of community in the urban areas, a basic error is often made to consider the house owners as the representative of the street, block or neighborhood, ignoring the individuals living as renters or people living in the squatters. This when done in a community level development oriented decision making process leads to basic and inherent flaw which dissipates the outcome of the development projects aimed at a particular household or community.

In the research not only the individuals and the area are important but also the inter relationship and interdependencies and interactions among them. This is because the internal structures of group/ community relation, informal organizations, NGOs/CBOs and the institutions have certain characteristics, which allow these social entities to act as a unique unit, which also means that individuals strongly influence community behaviors. Despite having a discrete structure, no two communities are exactly identical or having similar demands and need structures, occupation and organization.

Given this identification and description, “community as a group of people with some traditional structural ties and associations, can progressively transform their environment with the help of, but not allowing dominating external agents” (Oakely, 1991:161).

2.1.2 The Community Development (CD)

Community Development can be defined as the way in which a group of interested people deal with the threats and opportunities that affects their lives and living. It can therefore be described as a community driven development process that involves groups of people at the community level to come together to initiate collectively some action to improve their well being. In this vision of society, each individual accepts personal responsibility for the well being of the community and each other. The community development process takes place in the society, normally in a systemized and planned way; however it can also occur as a socially motivated act, often resembling a social movement though lacking the spirit and motivation/ emotional commitment of a social movement. According to Vansan (1970), CD as a movement is a way of returning to the people a greater measure of control over their destinies. Though seems utopian and optimistic, it is however clear that considering CD as a process tends to focus upon the dynamics inherent in the interaction among community members or household who seek to deal with community change, and such interaction is present whenever CD happens.

The concept of CD in the development field has primarily been associated with rural development efforts of the NGOs working in the developing and LDC countries and there has been a tendency to consider the community as a homogeneous unit, wrongly discarding all the intertwined intricacies of segregation and status due to caste, color gender etc. “little if any attention was paid to intra-communal differentiation based on class, gender and power (Wils & Rijn, 1988:8). They also argue that the process of CD is impeded by a variety of forces and factors that are inherent in the community. The value system, the interdependence of elements and dimensions, power, and the institutional and organizational structure of the community all serve to retard and undermine the process of change (Gittel, 1980:36). Yet at the same time these factors may also strengthen the process of development. Foster mentions that the Community Development Programmes (CDP) around in the third world countries have almost always been structured in a way that assume the third world communities in the rural area are a homogeneous unit. “An unfactionalised mass of cooperative persons who need only an outside catalyst to initiate community development activity (Foster, 1982:190)”.

2.1.3 The Community Participation (CP)

Participation first caught the attention of mainstream development agencies, grappling with how to make their interventions more effective, in the mid 1970s (Cohen & Uphof, 1980). By early 1980s, community participation had come to be associated with the sharing of benefits by the poor, project efficiency and effectiveness and cost sharing (Bamberger, 1986). By 1990s, mainstream development agencies uses of participatory approaches increasingly came to be couched in the language of the markets, constructing participants as consumers, users and choosers (Gaventa & Cornwall, 2001) and thus for many development agencies, stakeholders and ownership became the watchwords.

Focusing on the poor is one thing, bringing them together to actively participate in their own process of development is another (Bamberger, 1988:9). Participation means different things to different and the term is often used to describe anything from political empowerment to cost recovery in service provision (UNCHS, 1991). According to Dudley, with the realization that the scale of the problem is too big for the government to handle by conventional means, participation has become an economic necessity (Dudley, 1993:8). Thanks to the space created by the inability or limitation of the governments, many development agencies, NGOs, INGOs, INGDOs and similar institutions have started to use the CP methodology in their development programmes and they are actively engaging the local communities for the local economic development. Such organization as UN, UNDP, UNICEF, UNHCR, OXFAM, GTZ, USAID and many more are working with the assistance of grassroots organizations at the local level. Besides, World Bank and ADB as well as the local governments LGs have also devised methods and instruments and procedures which actively involve the local communities in the development practice.

The International Cooperation Administration for instance defines CP as “Process of social action in which people of a community organize themselves for planning and action, define their common individual needs and problems, execute these plans with maximum reliance on community resources and supplement these resources when necessary with service and material from government and non government agencies outside the communities (Foster, 1982:184)”.

Both the government and the non government development agencies consider CP in development as a cost effective and sustainable mode of development, the UNCHS believes that actively engaging community in projects would increase sense of responsibility amongst the community for operation and maintenance of resources, which will result in longer life span of physical assets (UNCHS, 1994). It is also to be considered that despite the success of self help and CP, government and development agencies often argue as to how much of the CP could be supported. The wrong assumption of development organizations while practicing CP has been about presence of structures existing where these efforts could be practiced. However, as Bawalya puts it, that even where such structures exist, they are very weak (Bawalya, 1985:183). In doing so it is also taken into account to incorporate local knowledge and skill as well as local resources in local economic development (McArthur, 1993). Various authors of development studies such as Oakely (1991), Esman & Uphof (I994) have mentioned numerous benefits of CP. Most of the authors on CP share another wrong underlying assumption about CP that it ensures equitable distribution of benefits meaning thereby that even the most marginalized groups in community will surely stand to get the benefits from physical resources. This however remains an elusive and desirable objective of the intended benefits of CP because general observations and experiences from development practices around the world indicate that CP is unable to change the power structures and issues of access to resources for the marginalized, children, women, old people, people without access to information still remain. Poorest of the poor still exist and the grassroots level power structures continue to produce inequalities in resource distribution. The basic theme of the research under hand also attempts to unearth these inequalities when it analyses the primary and secondary data of mid term M&E reports of SLBAP project.

Moser (1984) came closer in describing the tenets of CP by making a distinction between Participation as a “means” and as an “end”. She goes on to explain that participation as a means is considered as something or form to mobilize and get things done. This could either be state driven (Top Down mobilization) or Bottom-up, voluntary (community based) mobilization for development. Inadequate delivery mechanisms and lack of social structures of local coordination are obvious and prominent constraints which hinder participation. Where participation is identified as an end, the objective is not a quantifiable development goal but a process whose outcome is meaningful participation in the development process, where the aim is to increase control over local resources and regulative institutions. Moser (1991) goes on to admit that it is not the objective to evaluate participation as an end or as a means but identification of the process whereby participation as a means has the capacity to transform itself into an end. Participation here is not alone to be studied and analyzed as a management tool but also as a process for the community to take on responsibility of their development in whatever role society demands from them.

2.1.4 Participatory Governance (PG)

Participatory Governance (PG) for development is the core objective of this research. This approach provides basis for the concept of participation of citizens in a reconfigured space that exists between citizen and the institutions that affect their lives, particularly that of state (Gaventa, 2002; Cornwall, 2002). Exploring the interplay between invitation and demand and exploring how these new spaces for citizen participation are occupied, negotiated, subverted or mediated calls for a focus on dynamics not only within these spaces, but in others- from the arena of public meeting to that of home.

Participation first caught attention of mainstream development agencies, grappling with how to make their interventions more effective, in the mid 70s (Cohen & Uphof, 1980). By early 80s, Community Participation had come to be associated with sharing of benefits by poor, project efficiency and effectiveness and cost sharing (Bamberger, 1986). Beneficiary participation was a matter of pragmatism rather than principle to achieve cost effectiveness and compliance. And the best way of doing this was to organize local people in self help groups or committees through which they could have some input in project implementation. By 1990s, mainstream development agency’s use of participatory approaches increasingly came to be couched in the language of markets, constructing participants as consumers, users and choosers   (Gaventa & Cornwall, 2001) and thus for many development agencies, stakeholders and ownership became the watchwords.

The concept of participatory governance has its place in not only mainstream development but development practice as well (Schnieder, 1999). PG aims to overcome the asymmetry of information and agency by involving local people for more and full information and hence better outcome. This information is not only technical but social and political as well. So there is strong commitment as compared to top down models of development with better accountability.

Putting PG in practice involves changes in behaviors, bureaucracy, models of learning and analysis and action (more by locals and insiders). Chambers (1983) describes it “reversal of attitudes”. But this is not sufficient to ask a change in bureaucracy, it is equally important to de politicize development process as it is more damaging since the LG bureaucracy is subordinate to local political leaders. PG assumes that power structures can be changed and decentralization could be one quick way of doing it instead of pushing from the top. Empowerment, accountability and capacity building are the trilogy of PG and are inter dependent on each others as factors of success.

The analytical framework of this research looks at how and to what extent LGs behave in a manner as designed in the project and also facilitated in the local government system for citizens empowerment to play a role in development practice. The study has its dependant

Variable which are effective and actual empowerment of the communities for sustainable and improved livelihoods for the marginalized and the poor.

In the new decentralized LG system the concept of Governance has an embedded provision for enablement as a pivotal factor (Helmsing, 2000). The LG system provides legally enacted space for multi actor role for all the stakeholders in the local social and economic development practices. These administrative reforms were introduced realizing the fact that there are limited resources with the governments and therefore it is necessary to enable people to do something for themselves (UNDP, 1990 p-92). As a result of these reforms legal, administrative, financial and public planning frameworks are in place to undertake collective action by LGs and communities have been institutionally empowered to participate in development practices. (Helmsing, 2000), (Smith B, 2000).

The term Participatory Governance has emerged in the late 1990s from the concept of “Good Governance” and has its place in not only mainstream development thinking but development practice as well (Schnieder, 1999) and is considered an important link in net causalities to be taken into account  in developing and implementation of poverty reduction strategies. This is for the wrong assumption in GG about non existence of the problem of “information” and “agency”. PG tries to overcome this problem by involving others, based on the rationale that full information leads to better outcomes.

2.1.5 Decentralization-Development and Poverty Reduction

Globalization has brought about unprecedented growth in human development but not without growing socio-economic divide. Growing political globalization has made democratic governance spread more widely. Achievement of certain development criteria as set out in the United Nation Development Programme (UNDP), popularly known as Millennium Development Goals (MDGs) regarding trade, healthcare, education and environment, demands and hinges largely on society’s quality of governance and good governance includes respect for human rights, political openness, participation, tolerance, administrative and bureaucratic capacity and efficiency, creation of effective partnerships to ensure that political, economic and social priorities are based on broad consensus in society and voices of the poorest are also heard in decision making process.

Decentralized governance if planned and implemented offers opportunities for development. Devolving some political, administrative and fiscal authority to sub national level/district level develops a system of shared responsibility between institutions at central and local level, thus increasing quality and effectiveness of the system of governance. Decentralization strengthens both central and local governments and also creates. It brings decision making closer to the people and thus yields programmes and services that better address local needs.

One of the compelling arguments for Decentralization is the natural advantage that District Governments have as compared to CGs in achieving a good match between the public good supplied and preference of population. This fit, however can only be obtained if LGs have mechanisms in place that permit their inhabitants to hold public offices accountable through democratic elections and properly communicate their preferences to decision makers through community participation. Decentralization is restructuring of authority so that there is a system of co responsibilities between centre, and local level of government. Political decentralization is called devolution and administrative decentralization denotes deconcentartion and delegation of powers. Since the reforms have been introduced there are about 80 countries who have adopted some kind of decentralization reforms. Until 1999, 96 of 127 countries were politically decentralized and another 41% had fiscal reforms introduced.

Decentralization should have a positive impact on poverty reduction, by making voices of poor heard and improve their access to resources thus reducing vulnerability. However, study of various LGs around in Africa and Asia; it has been observed that decentralization has led to improvement in poverty reduction in one third countries, thereby contradicting the notion of nexus between the two.

During 1990s when reforms were in full swing, many fiscal and economic policy makers at CG level joined forces with political reformers in supporting decentralization reforms. A broad consensus on benefits of decentralization saw improvement in citizen participation opportunities and political accountability and secondly reforms for a more responsive allocation of public resources. At CG level, governments were expecting more financial benefits from structural adjustment goals that many countries had committed themselves for.

Decentralization reforms have so far been unable to achieve rather elusive objectives of participation for development, accountability and expenditure reduction. The later has been especially been exaggerated. On the contrary, devolution has been proven to be very costly both technically and politically. Whatever downsizing gains were anticipated was quickly swept away by increasingly indebted LGs who failed to raise their revenues one after the other.

2.1.6 Devolution of Power

The term devolution is commonly used to refer to those situations in which a previously unitary state distributes powers to other territorial units. Simply defined devolution is a practice wherein the authority to make decisions in some spheres of public policy is delegated by law to local level. Thus devolution entails a transfer a government or political authority in which powers of the constituent units is determined by legislation rather than constitution. In theory devolution can occur in both a federal and a unitary system of government. So long as a mechanism is put in place to mediate and facilitate transfer of power, responsibilities and resources from CG to elected LGs.

According to Dr Peter Wayande (2001), devolution is defined as a political process that denotes transfer of political, administrative and legal authority, power and responsibility from the centre to the lower levels of government created by the national constitution. The devolved units created are more or less autonomous from each other. They are also free from the influences of CGs. With a clear jurisdiction and out side direct control of CGs, devolved political units are the true form of decentralization, democratic decentralization, local autonomy and self governance.

Rationale behind devolution is multi facet objectives of differentiated and pluralist structure of government, grassroots political process, participatory bottom up development, sustainable development, appropriate planning and implementation, harboring nursery of local leadership building and local and institutional resource base.

Pakistan government launched a campaign for political devolution in 2000 that it said was aimed at transferring administrative and financial power to local governments. The scheme

was to strengthen local control and accountability and, according to President Pervez Musharraf, "empower the impoverished".

Under the Devolution of Power Plan announced in August 2000, local governments were to be elected on a non-party basis in phased voting between December 2000 and July 2001. District and sub-district governments have since been installed in 101 districts, including four cities. Operating under its respective provincial Local Government Ordinance 2001, each has its Nazim and Naib Nazim (mayor and deputy mayor), elected council and administration.

Talking of experience in devolution in Pakistan, Devolution, in fact, has proved little more than a cover for further centralised control over the lower levels of government. Despite the rhetoric from Islamabad of empowerment, local governments have only nominal powers. Devolution from the centre directly to the local levels, moreover, negates the normal concept of decentralisation since Pakistan's principal federal units, its four provinces, have been bypassed.

A study of devolution reforms around in African and Asian countries also corroborates the negative and reverse impact of devolution attributed mainly to lack of political commitment, formalism vs. Realism, lack of institutional and resource capacity, patron client relationship and absence of active citizen participation.

2.2. Analytical Framework

The main objective of this research has been to evaluate the extent to which the LGs have been instrumental and effective in performing their role for project goals. The study has its dependent variable as “effective and actual empowerment of communities “and for assessing this, independent variables of  LG institutional setup, LG capacity to influence to convene actors and power of decision making will be tested. Apart from the above independent variables, the project framework for participatory action will also be analyzed.

2.2.1 Political Party Constellations

The influence of politics in local governance is likely to have a considerable impact on LG performance. For the purpose of this study and because politics are vast and all embracing, only issues related to political will, political party relationships and influence on local party decisions (party composition, opposition versus party in power at the centre or party composition at the LG level), LG internal decision making processes and electorates influence on decision making will be discussed. Furthermore finding in the research about LG in Israel support the growing evidence of interaction between CG and local decision makers critically important in shaping the social programmes delivered at LG level (Asford, 1990). Furthermore, relationship of the CG with the same party LG and with opposition parties, LG may contribute or hinder effective local governance. It is important to recognize that LG relation is also influenced by political parties constellations whether from their political parties or from the opposition in case of majority in the assembly.

2.2.2 LG Institutional Set up

According to Grindle (1997) the institutional context of public sector includes rules and regulations/procedures set for government operations and public officials	, financial resources. Government has to carry out activities, responsibilities that government assumes for development initiatives, and concurrent policies and structures of formal and informal influence which affect public sector functions. Grindle states that the structures, goals, working procedures, defined authorities and relations provide incentives for development initiative. These factors can promote or constrain performance of organization.

This analytical section also deals with relationship of dependent and independent variables of research, main aspect and indicators needed to measure effectiveness of community enablement and participation in the LG and project design.

| variables | Main aspects | Indicators |
| --- | --- | --- |
| LG institutional setup Influence of politics in decision making | - Effective accountability mechanism - M&E system - National party influence on LG leadership - Local ruling/opposition party influence on leadership - LG internal politics influence on policy management and implementation - Electorates influence on decision making | - Legal/constitutional form of LG - Legislation with powers - Legislation addressing gender issues - Recognition of community in decision making - Written rules and procedure - Internal and external accountability mechanisms - Internal and external monitoring and evaluation procedures - State of relationship between CG and LG - LG assembly ruling/opposition party deliberate, influence and adopt right policies - Extent of officials participation in decision making - List of CBOs and degree of involvement in policy process |

2.2.4 LG Capacity to Ensure Participation

| Variables | Main aspects | Indicators |
| --- | --- | --- |
| LG Decision making capacity LG Capacity to convene other actors | - Political will - legitimacy - degree of accountability - plan for CBO participation - coordination - efficiency - efficacy - sustainability - transparency - LG increases its resources needed by local community - Efficiency to convene actors - Capacity factor - Equity assurance - Transparency - Sustainability of action to convene | - degree of accountability from CG to LG - priority setting whether LG will work alone or involve CBOs - internal mechanisms for coordination between different planning offices within LG set up - specific planning activities of CBOs for planning, consultation and decisions - list of CBOs involved - types of community plans - legal framework with clear function of managers and politicians - guidelines on new working procedures - managers effectiveness - framework for recruitment - incentives for employee retention i.e. pay, promotion, training etc - list of programmes and schemes completed in time - LG rules provision - Formally recognized community role - NGO/CBO registration - Comparative community associated project study - List of various actors - LG partners - Level and extent of flexibility - Timely availability of information - List of schemes |

CHAPTER THREE: SOCIO-ECONOMIC AND DEMOGRAPHIC PROFILE OF THE PROJECT AREA/DISTRICTS

- Introduction

This chapter provides socio-economic and demographic profile overview of the project area which comprises of ten (10) districts of the Province of Punjab, Pakistan. This selection has been made by the project for being predominantly rain water dependent areas for agriculture practices by farming communities, as well as for drinking water. The data on profile has been adopted from the baseline survey conducted by the ADB. The research, using this data, opens up general condition of rural farming as well as non farming communities with the help of detailed base line surveys of communities and households. A further understanding about characteristics of livelihoods of rural communities in Barani Areas (Rain fed) of Punjab province in terms of their assets and opportunities is important for research purpose when evaluating outcomes in terms of physical achievements of the project intervention. Using formal and informal sampling techniques of Participatory Reflection and Action (PRA), Group Discussions (GD), Key Informant Survey (KIS), Direct Observations, Transect Walks, Triangulation methods, basic information about project villages and communities has been collected from the area.

In the second stage of the survey, two villages from each union council of the all the project district (one far from the main town and the other from remote area) were selected. The survey also selected one non project village from the area. It is pertinent to mention here that selection of a particular beneficiary community was based on a bench mark principle i.e. areas with more than 75% agriculture depending on rain water and having no irrigated canal water available.

Table 2: SLBAP sample Districts, Tehsils, Union Councils, Villages and sample size

| S.No. | Districts | Tehsils | Union Councils | Villages | sample size (male & female) |
| --- | --- | --- | --- | --- | --- |
| 1 | Rawalpindi | Kotli Satian | Deer Kot Satian | I.Dheer Kot Ii Dheer Kot Satian | 44 46 |
| 2 | Chakwal | Choa Saidan Shah | Sanghi | I.Sagral Ii.Mhiwal | 44 42 |
| 3 | Jhelum | Dena,Jhelum | Basharat | I.Parala Ii.Jangoo | 46 42 |
| 4 | Gujrat | Kharian | Kunjah | I.Chak Akhlas Ii.Jeteria | 44 42 |
| 5 | Sialkot | Pasrur | Bajra Ghuri | I.Anola Ii.Selu | 42 40 |
| 6 | Narowal | Narowal | Mararah | I.Wazir Pur Ii. Lial | 42 44 |
| 7 | Khushab | Nor Pur Thal | Rang Pur | I.Chak 42 Ii.Chak 45 | 48 46 |
| 8 | Mianwali | Esa Khel | Chapri | I.Chapri Ii.Kotki | 42 48 |
| 9 | Bhakar | Bhakar | Sial | I.Hussain Abad Ii.Shahani | 40 44 |
| 10 | Layyah | Layyah | Kot Sultan | I.Jam Rid Ii.Ahmad Yar | 40 42 |
| Total | 10 | 10 | 10 | 20 | 868 |

In the third stage households (HHs) were selected proportionally and randomly from each stratum based on poverty levels which were selected through PRA technique.

3.1.1  Access to Land (Ownership, Rented, Shared)

The survey by SLBAP about economic profile of the area and communities in rain fed districts revealed 70% HH relying on agricultural practices i.e. cultivation while rest of 30% community is also engaged  in activities which could be termed non agriculture yet are closely associated and dependant on agriculture. The comparative number of HH dependant upon agriculture in non project area is higher which shows relative high rate of dependence of HH of non project areas on agriculture, which is obvious for access to more irrigation water as compared to rain fed areas (Table 3)

| Table 3: Agriculture And Non Agriculture HH In The Project And Non Project Area |  |  |  |
| --- | --- | --- | --- |
| Categories | Agric. HHs | Non-Agric. HHs | Overall |
| Project Area | 67 | 33 | 67 |
| Non Project Area | 73 | 27 | 33 |
| Overall Area | 70 | 30 | 100 |

As per survey, average HH land ownership in the project area is recorded as 34 Kanals in SLBAP area as compared to the overall average of 30 Kanals. The overall tenure status is predominantly ownership based with 85% HH having their own land for agriculture. The rest is tenant and owner cum tenant, each at 6.5%.

As per survey conducted by the project team, average family sizes observed in HHs was 7.6%. Dependency ratio was assessed at 67%, with female ratio reported to be a little higher than overall average. The overall adult literacy rate amongst male was 78.45% and female was 43.65%. Overall, the rate was 77.9 and 49.7% amongst male and female, respectively.  The overall as well as adult literacy rate was found highest 95.5% and 73.3%, 96.9% and 69.1% amongst male and female in Rawalpindi area, respectively. It was reported lowest in Sialkot area. On overall basis among male and female age less than 15 years 6.1% and 3.9% were unemployed respectively. This ratio was high 66% in males as well as in female 72% having age 15-60 years. About 28% of male and 48% of female have age greater than 60 were unemployed. On overall basis among agriculture 37% were male and 27% were female.

3.1.2 Poverty in the Barani Areas

Poverty reduction in the developing countries is considered to be the yard stick for gauging development. There has been a sharp rise in poverty in 1990s, after a prosperous run of high economic growth in 70s and 80s. Over the past 5-6 years, Pakistan has made a considerable progress; the real GDP has grown at an average annual rate of over 7 percent and the real per

capita income has grown at an average rate of 5.6 percent per annum. An improvement in the employment situation has also been witnessed. The inflows of foreign remittances, particularly from the USA after the 9/11 event, have reached to record high levels. All these factors have led to a significant reduction in poverty levels in both urban and rural areas of the country.

However, despite a more than 10 % decline in poverty levels between the 2001 and 2005 period, poverty reduction remains the main development challenge as 28 % of the rural population lives below the poverty line. In these studies, the lowest levels of poverty are consistently found in barani Punjab consisting of four districts: Rawalpindi, Chakwal, Jhelum and Attock while southern Punjab and rural Sindh are assessed as the poorest regions of the country. Low levels of poverty in Barani areas do not mean that poverty is non-existent in this region. It is only in relative term; the fact is that during the whole decade of 1990s around one-fifth to one-quarter of the barani population was poor, living below the poverty line. These poor may be at disadvantage than other rural populations because of fewer employment opportunities available in the agriculture sector of barani areas. Poverty levels in the project and controls areas of the SLBAP are examined by using the household survey data carried out in these areas in 2007.

Using the PIHS method in 1998-99, Government calculated the absolute poverty line of Rs 673.5 on 2350 calories per adult per day by using caloric approach. In 2004-05 it was reported at Rs 878.6. For SLBAP project in 2007, this poverty level was estimated at Rs 1023 after adjusting the CPI and this has been used as a base for the project. Further, in order to understand various levels of poverty in the project areas, a new band model has been used to identify the population in different groups such as extremely poor, vulnerable and non poor etc. The sampled population is divided into six groups; extremely poor are those individuals with less than 50% of the consumption level of the poverty line i.e. Rs 512 per month. Ultra poor are those with more than 50% but less than 75% of the consumption levels, while poor and vulnerable are about the poverty line and non poor well above it as per table below.

| Table 4: classification of population by poverty status (poverty line Rs 1023 per month) |  |  |
| --- | --- | --- |
| Poverty Status | % of Poverty Line | Poverty Lien Rage in Rupees |
| Extremely poor | 50% | Rs. 511.5 |
| Ultra poor | 50% 75% | Rs.511.5 – Rs.767.25 |
| Poor | 75% 100% | Rs.767.25 – Rs.1023.0 |
| Vulnerable | 100% 125% | Rs.1023 – Rs.1278.75 |
| Quazi-non-poor | 125% 200% | Rs.1278.75 – 2064.0 |
| Non-poor | 200% | Over Rs.2064.0 |

The incidence of poverty in the SLBAP project area and the control areas was estimated by a survey before the launch of the project and it was interesting to note that in the 10 project districts in 2007 the incidence of poverty was 19.2 which meant that about one fifth of the population was living below poverty line where as in the control area this poverty level was 24% meaning thereby that the project district population was better of as compared to the non project areas

| Table 5: Head count ratios- % of population poor by zone and project and control areas |  |  |  |
| --- | --- | --- | --- |
| Zones | Project areas | Control areas | All |
| All Areas | 16.7 | 24.3 | 19.2 |
| Rawalpindi zone | 14.5 | 17.9 | 15.6 |
| Sialkot zone | 20.1 | 27.5 | 22.6 |
| Mianwali zone | 15.8 | 25.8 | 18.9 |

Source: SLBAP Survey, 2007

3.1.3 Gender Role

Women are the most vulnerable segment of society and gender relations are interwoven into broader set of social relations structuring division of resources and responsibilities, claims and obligations between different social groups of men and women. These take a crucial role in gender responsive governance and rights based approach for equitable social development.

It is important to know as to who takes decisions on various important matters concerning social and economic bearing on the family. It was interesting to note and see the impact of these decision making empowerments and authorities in the survey of project areas. Survey revealed that decisions like marriage and solving disputes were done mainly by male (58%). Interestingly, supervision of HH was done substantially by male 31%, female 35% and by wife 25%. Overall, women see to play lesser decision making role in all the affairs of the HH, compared to husbands which showed a typical social trend of male dominance. It was interesting to observe during survey that women participation in farm and agriculture activities was made and rather imposed upon them by males (46%) and only 3.4% of the females responding to this question reported that they were doing it at will. Female share in the family income was substantial and the source of income included milk/ghee/egg selling, sewing and other activities. Through their income, females are able to make savings in cash, jewellery and live stocks and others. Substantial number of women reported availing loaning facilities for using in income generation.

CHAPTER 	FOUR: EVALUATING PARTICIPATION AND ASSESSING PROJECT ACHIEVEMENTS FOR POVERTY REDUCTION

4.0 Introduction

Devolution, decentralization and decentralized governance refer to the restructuring and re organization of authority so that there is a system of co-responsibility between institutions of governance at central, regional and local levels (Piracha, 2003). According to the principle of subsidiary local authorities, with powers to address local issues and problems which are within their capacity to solve and hence increasing quality and effectiveness of the system of local governance, were to increase capacity of LGs. There were three underlying objectives behind LG reforms in Pakistan. Service Delivery was considered as foremost while it was argued that LGs properly empowered, staffed and resourced would deliver better on primary health, education, provision of municipal services and agriculture extension. Secondly, devolution was considered to improve the ways laws about property and labor rights and economic activities were determined and enforced. For this reason LGs were given responsibilities to regulate and administer laws on land, labour and natural resources, NGOs and commercial enterprises. The third and rather less appreciated was conception that LGs would be a source of “access to justice” where it was believed that local administration, the courts, and the police would all improve, that basic human rights will be better recognized and protected under devolution (Charlton, 2003).

Devolution or decentralization and development of Local Government Institution are the responsibilities of the Government of Pakistan. The Article 32, of the Constitution of Pakistan stated (Government of Pakistan, 1973):

“The State shall encourage Local Government Institutions composed of elected representatives of the areas concerned and in such institutions special representation will be given to peasants, workers and women.”  .

Local Government Ordinance (LGO) introduced the Local Government system in Pakistan in August 2001. Already, the devolution has spent a significant period. It is important to know what is going on in this connection.

4.1 People’s Perception of Devolution

Already, devolution has had some time in Pakistan and LGs are about to complete second generation local governments in Pakistan and the system has been under debate on various thresholds of performance, political will and institutional and policy/regulatory considerations. As such it is vital to understand people’s perception with special references to basic amenities of life, status of service delivery and the built mechanism of community participation and community enablement structures as laid down in the devolution plan.

An interesting survey about how people perceive devolution to be useful and effective in solving their problems and making and creating space and empowering community for an active role play for provision of basic services and for solving local problems particularly related to resource provision and generation leading to economic betterment and poverty reduction.

It was responded by 89% of the surveyed HHs that roads were developed in their areas as a result of devolution and establishment of LGs in the districts and remote rural areas. About 43% responded that water supplies were provided to these areas by LGs. same was the response for health and education services in the remote rural areas.

| Table 6: Devolution and People Perception (Basic Amenities) in the Project, Non Project and Overall Areas in Barani Punjab (%age). |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Categories | Roads | Water Supply | Electric. | School | Hospital | Medical | Any other |
| Project Area | 90.3 | 47.3 | 30.8 | 22.1 | 7.5 | 7.2 | 19.4 |
| Non Project Area | 82.9 | 26.1 | 40.0 | 34.3 | 20.0 | 1.4 | 8.2 |
| Overall | 88.6 | 42.3 | 33.0 | 25.0 | 10.5 | 5.8 | 16.9 |

Similarly, in the service sector HHs reported increased opportunities of employment, input supplies, livestock services and justice.

4.2 Local Government and Community Participation

Under decentralization reforms, LG system has its own embedded and institutionally enabled system for participatory development called “The Citizen Community Boards” with exclusive and earmarked financial resources and politically and administratively supported mechanisms in place since 2001, which dissipates the notion that LGs were estranged to the participatory processes. The CCB mechanism had an almost identical set of obligations on part of the LG and the beneficiary i.e. equity of cost sharing of 80-20. The LG data on CCB fund utilization and number of projects completed also gives strength to some biases towards the SLBAP project. There is no denying the fact that LGs also have serious issues of capacity in terms of shortage of staff, untrained personnel, and typical “slow moving” beaurocratic mechanisms which curtail development rather than facilitating it. For a better understanding of the project approach of involving the institutional mechanism of LG for project implementation, it is imperative to study the LG community participation role for local economic development which is demand driven as well as participatory.

John Stuart Mills argues that the democratically elected institutions of local governance are necessary for people participation. For the fact of being local and having local knowledge, they are best suited for local development. A more recent concept in the Local Governments is citizenship (Soledad Garcia 1996, Hill 1994).The word Citizenship is used in somewhat different context to grip on governance issues linked with diversity especially cultural and ethical diversity. It is also used for accessibility and equality issues to counter marginalization and exclusion as well as political rights (Marshal, 1964)

4.3 Union Council Development Component (UCDC)

Implementation Mechanisms

As enumerated in the previous chapters, UCDC component has been designed in the project for a pivotal role of the LGs. As such, the ten (10) District Governments (DGs) has been assigned management and day to day handling of affairs in the project. DGs will however be assisted by the project staff posted in the districts as District Project Managers (DPMs) and District Project Assistants (DPAs). Support from international technical experts and a local consultant was also envisaged.

Implementation Cycle of UC Development Component

| Sr. No. | Steps / Process Involved |  |
| --- | --- | --- |
| 1 | # Need Identification Process at the Grass Root Level - Create awareness - Facilitation for needs identification (role of SLBAP project facilitators for creating awareness among organized communities would be vital). - Infrastructural and non-infrastructural socio-economic developmental activities. - Prioritization of needs - Prioritization and ranking of needs portfolios |  |
| 2 | ## Preliminary Appraisal and Approval by UCs - District /Tehsil government will provide guidance and support to the UC to conduct viability. |  |
| 3 | # Role of District Development Committee (DDC) - DDC will perform coordination role & preparation of PC-I form. Community will be consulted while preparing PC-I form. - Approval of scheme - The scheme will also be approved by the SLBAP. - Ensuring M&E |  |
| 4 | The Executor of Scheme The following criteria will help to make decision about the executor of a scheme. - The nature of scheme - The financial size of a scheme - The capacity and capability of the NGOs, CCBs or Communities ###### CCBs - New CCBs formation or use of already registered CCBs for the identified/ specific scheme. - Capacity building of CCBs for preparation of the proposal, implementation and M&E. - Completion of Form -IV and related formalities /formats of funding release etc. - Signing of agreement Form-V between Department and CCBs |  |
| 5 |  | Role of Line Department - Technical viability. - Social viability (with reference to the short term or / and long term benefits of an activity or scheme). - Economic viability (the income /employment expected and other tangible benefits). - Environmental viability as per requirement of EPA standards (applicable to certain size of schemes only). - Analysis on account of gender and development aspects of a scheme. ### The contractors’ profit aspect in the cost estimates of the scheme. - The provision of withholding /income tax in the cost estimates. - Financial and performances audit of the schemes. - The responsibility for maintaining the measurement books of the scheme. # The estimates on account of the O&M of a scheme |
| 6 |  | Essentiality of PC-I Form - All executing agencies including the line departments, CCBs or the COs /NGOs will adhere to the approved PC-I form at the time of physical implementation of a scheme. - Like wise, while implementing scheme through CO, the project proposal/sketch of a CO can be annexed with approved PC-I form. |
| 7 |  | #### MoU with District /Tehsil Government, UCs / CCBs / CO and SLBAP - MoU between SLBAP and UC/tehsil/district. - Terms of Partnership (TOP) or Agreement (Form-V of CCBs) among SLBAP, CCBs and line department. - TOP among SLBAP, line department and CO. |
| 8 | #### Release of Funding & Physical Implementation ##### Cost of scheme in lump sum or in instalments to be decided as per the approved PC-I form or the CCBs form - Support to district line agencies. #### The concerned department/sub-department will render full support |  |
| 9 | ###### Monitoring & Evaluation of the Scheme - M&E by line department of district / tehsil or other executors - M&E by ZMC / TMC concerned - M&E by SLBAP - M&E by funding agency - M&E by concerned beneficiaries #### The monitoring of a scheme will be conducted according to the guidelines of Activities to Output Monitoring (ATOM) system. SLBAP Project Facilitators (PFs) will revise the information sheet in consultation with the DPM. |  |
| 10 | # Completion of Project The concerned line department will carry out necessary monitoring /evaluation and issue a completion certificate regarding any scheme as per the procedure in vogue. |  |
| 11 | # Ownership and O&M Responsibility The ownership and the responsibility regarding operational arrangement repair and maintenance of any development scheme would be decided at the time of preparation of proposal, PC-I |  |

The approval process for a proposal is subject to certain guidelines detailed for the line agencies as well as the community to adhere to in identification of the intervention, which are as under:

- The estimated cost of the activity will generally be at least $25,000 (Rs.1.5 million).

- The proposed beneficiary contribution and how it will be made will be clearly spelled out. At least 5% of this will be as an up-front payment made into a separate account. The balance may be made in kind with materials and labour.

- The proposed operation and maintenance arrangements will be clearly spelled out. In some cases (for example small scale water resources infrastructure or jeep able tracks)

- The proposal checked against the environmental impact framework checklist

- The proposal will be checked against the social impact framework checklist

- The proposal will be deemed technically feasible by the relevant district line agency.

- The degree of support to be contributed by the relevant line agency and the amount of strengthening, if any, required by it will be clearly spelled out.

- The minimum number of beneficiaries for each intervention under the Union Council Development Component will be 100 families.

For the implementation of the approved proposals, a Memorandum of Understanding (MOU) is signed between ABAD and the Union Council detailing the degree of beneficiary contribution, the commitment by the Union Council and the beneficiaries to operate and maintenance, the commitment by the Union Council to environmental and social mitigation if required and the role of the Union Council and the beneficiaries in monitoring implementation. Another Memorandum of Understanding is signed between the District and ABAD detailing the amount of funds to be provided, the role of the line agency in implementation, the implementation arrangements and schedule and the role of the district, if any, in operation and maintenance.

4.4 Implementation Progress of SLBAP

The SLBAP project is in its fifth year and the pace of development and physical progress has been improving gradually and to some extent making up for the bottlenecks faced in the start due to LGs role and confusions about authority and created spaces for community role in the project in real terms where beneficiaries are supposed to be playing roles right from the identification stage through to active role in execution and ownership of the physical and financial assets of the intervention. Significant union council development interventions have been undertaken by some 1800 communities and villages representing some 37000 HHs in 200 UCs. Key achievements include development of system and procedures for planning and implementation of MSIs and transfer of funds to line departments, CBOs completing 134 of the 618 MSIs (22%), while 62% at the approval stage by June, 2009. By now, 20% of the village population is part of the CBOs showing interest in participation by HHs in the project. The line departments have been made functional in providing support to communities. Rural support NGOs assisting in the project have been able to strengthen and upscale their outreach and facilitate target groups to initiate poverty focus initiatives.

4.4.1 Financial Progress

Under the UCDC component during year 2008-09 a sum of Rs 186.7 million was allocated out of which a sum of Rs 178 million has been spent which shows significant utilization and underpins the earlier reservations about the implementation mechanism as workable. This remarkable progress is depicted in the table below and is clearer when compared to cumulative progress and year wise performance shown in the subsequent tabulated data.

Table 7: Cumulative Status of Medium Scale Interventions (MSIs) from 2006-09 as of June,

| Sr # |  |  | District |  | Approved by the UCs |  | Submitted to district govt., |  | PC-I prepared |  | Approved by DDC |  | Under Impl. |  | Schemes Completed |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  | Rawalpindi |  | 27 |  | 19 |  | 10 |  | 7 |  | 2 |  | 1 |  |
| 2 |  |  | Jhelum |  | 63 |  | 61 |  | 54 |  | 36 |  | 7 |  | 17 |  |
| 3 |  |  | Chakwal |  | 52 |  | 50 |  | 29 |  | 15 |  | 5 |  | 3 |  |
| 4 |  |  | Gujrat |  | 106 |  | 106 |  | 59 |  | 45 |  | 5 |  | 20 |  |
| 5 |  |  | Sialkot |  | 100 |  | 100 |  | 100 |  | 42 |  | 4 |  | 14 |  |
| 6 |  |  | Narowal |  | 147 |  | 111 |  | 76 |  | 61 |  | 16 |  | 21 |  |
| 7 |  |  | Khushab |  | 121 |  | 121 |  | 59 |  | 53 |  | 20 |  | 16 |  |
| 8 |  |  | Mianwali |  | 128 |  | 94 |  | 54 |  | 45 |  | 5 |  | 8 |  |
| 9 |  |  | Bhakkar |  | 96 |  | 81 |  | 57 |  | 47 |  | 13 |  | 24 |  |
| 10 |  |  | Layyah |  | 67 |  | 43 |  | 36 |  | 33 |  | 10 |  | 10 |  |
|  |  |  | Total |  | 907 |  | 786 |  | 534 |  | 384 |  | 87 |  | 134 |  |
| Sr. No | District |  | Schemes Identified |  | Approved by UC |  | PC-I Prepared |  | Approved by DDC |  | Under Impl. |  | MSIs Completed |  |
| 1 | Rawalpindi |  | 0 |  | 2 |  | 3 |  | 0 |  | 0 |  | 0 |  |
| 2 | Jhelum |  | 1 |  | 16 |  | 30 |  | 12 |  | 0 |  | 5 |  |
| 3 | Chakwal |  | 5 |  | 20 |  | 9 |  | 0 |  | 0 |  | 0 |  |
| 4 | Gujrat |  | 30 |  | 34 |  | 30 |  | 16 |  | 4 |  | 3 |  |
| 5 | Sialkot |  | 20 |  | 46 |  | 65 |  | 21 |  | 0 |  | 9 |  |
| 6 | Narowal |  | 17 |  | 26 |  | 26 |  | 23 |  | 5 |  | 9 |  |
| 7 | Khushab |  | 45 |  | 11 |  | 15 |  | 14 |  | 10 |  | 0 |  |
| 8 | Mianwali |  | 19 |  | 33 |  | 8 |  | 10 |  | 0 |  | 2 |  |
| 9 | Bhakkar |  | 6 |  | 6 |  | 10 |  | 9 |  | 5 |  | 4 |  |
| 10 | Layyah |  | 0 |  | 0 |  | 12 |  | 12 |  | 5 |  | 4 |  |
|  | Total |  | 143 |  | 194 |  | 208 |  | 117 |  | 29 |  | 36 |  |

Table 8: Status of Medium Scale Interventions (MSIs) during this Quarter

Most of the delays were attributed to slow movement in project processing, delay in transfer of funds and contract awards. Further slow liquidation of advances by DGs, delay in recruitment of staff for project offices in the districts and consultants in the PMU were also considered as bottlenecks. Based on the performance evaluation surveys conducted in the ten districts these districts have been ranked for performance by the project office.

Table 9: Ranking of Districts as of June 2009

| Sr.No. | District | Target | Approved by DDC |  | Under Implementation |  | Completed |  | Cumulative Progress |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No | % | No | % | No | % | %age | Ranking |
| 1 | Bhakkar | 54 | 47 | 87% | 13 | 24% | 24 | 44% | 52% | 1 |
| 2 | Layyah | 39 | 33 | 85% | 10 | 26% | 10 | 26% | 45% | 2 |
| 3 | Narowal | 87 | 61 | 70% | 16 | 18% | 21 | 24% | 38% | 3 |
| 4 | Jhelum | 54 | 36 | 67% | 7 | 13% | 17 | 31% | 37% | 4 |
| 5 | Chakwal | 21 | 15 | 71% | 5 | 24% | 3 | 14% | 37% | 5 |
| 6 | Khushab | 87 | 53 | 61% | 20 | 23% | 16 | 18% | 34% | 6 |
| 7 | Sialkot | 69 | 42 | 61% | 4 | 6% | 14 | 20% | 29% | 7 |
| 8 | Mianwali | 75 | 45 | 60% | 5 | 7% | 8 | 11% | 26% | 8 |
| 9 | Gujrat | 105 | 45 | 43% | 5 | 5% | 20 | 19% | 22% | 9 |
| 10 | Rawalpindi | 27 | 7 | 26% | 2 | 7% | 1 | 4% | 12% | 10 |
|  | Total | 618 | 384 | 62% | 87 | 14% | 134 | 22% | 33% |  |

The cumulative performance measurement on financial and physical terms for the past five years show gradual improvement in project objectives and depicts a typical trend of growth which is evident in participatory projects. However the achievements shown are certainly not a depiction of the ideological attributes of ownership and characteristic of a demand driven intervention. For analyzing this aspect, one has to see the LGs institutions performance Vis-a- Vis LG own development efforts and utilization of funds, for which the following chapter uses the comparative analysis of the LGs and the project.

Table 10: Financial Progress

| Cumulative Expenditure against allocation (Rs. In Million) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Year | Allocation |  |  | Expenditure |  |  | % of Utilization against allocation |
|  | Govt. of Punjab | Asian Dev. Bank | Total | Govt. of Punjab | Asian Dev. Bank | Total |  |
| 2005-06 | 89.683 | 43.000 | 132.683 | 19.959 | 73.203 | 93.162 | 70% |
| 2006-07 | 94.694 | 223.093 | 317.787 | 94.683 | 191.795 | 286.478 | 90% |
| 2007-08 | 96.521 | 414.639 | 511.160 | 96.528 | 318.858 | 415.386 | 81% |
| 2008-09 | 86.712 | 300.000 | 386.712 | 80.405 | 285.710 | 366.115 | 95% |
| Cumulative up to June , 2009 | 367.610 | 980.732 | 1348.342 | 291.575 | 869.566 | 1161.141 | 86% |

Table 11: Overall Utilization against Total Allocation

| Sources | Allocation | Utilization | %age |
| --- | --- | --- | --- |
| ADB Share | 2460.00 | 869.566 | 35% |
| Govt. of Punjab Share | 516.00 | 291.575 | 57% |
| Total | 2976.00 | 1161.141 | 39% |

`

CHAPTER 	FIVE: FINDINGS AND CONCLUSIONS

5 Introduction

The lessons learnt from various concepts and notions already well established as well as new findings from the research reveal interesting facts that go beyond theoretical conceptualizations about community participation and empowerment/enablement. They tend to explain reality differently. Local Government institutional setup of CCB has been in practice in Pakistan and engaging communities for active role, ownership and sustainability of the effort. However, the evidence from ADP fund utilization in the ten districts when compared to CCB funding and execution, it was observed that there was not only reluctance and resistance on part of the Beaurocracy and political leaders, but the community was also hesitant to come forward. This could perhaps be due to a number of factors as confidence on LG officials, capacity to financially contribute, incapacity to act, lack of training, lack of information. The secondary data from project districts depicts certain complexities about SLBAP project of which issue of ownership stands out to be of significant value as empirical study of various issue suggests. It is a fact corroborated from development statistics that SLBAP project could not kick off in real terms at least till one year after its launch in 2005. The first time project funds were not used until in 2006 and that too after many requests to LGs officials and political leaders.

This research studied empirical data from project area and secondary data from LGs offices and project SLBAP with an attempt to find answers to the following research questions:-

- Did all the actors behave in the manner they were desired in the project design?

- To what extent did LG participation mechanism of enablement help facilitate the project approach of aligning LGs with the project?

- How did various actors behave in project implementation?

- Whether development was de politicized?

5.1 The Evidence, a- Case Study of District Khushab

Taking as reference a case study of District Khushab where SLBAP project is being executed in 31 of the 50 UCs since 2005, LG has had to face a lot of resistance at all levels from officials of DG to heads of UCs, Tehsils as well as District head who had his own considerations of political choice and favoring his supporters and voters.

Table 12: Development Fund Utilization in Khushab (Rs in million)

| Development programme | 2005-06 |  | 2006-07 |  | 2007-08 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Allocated | Utilized | Allocated | Utilized | Allocated | Utilized |
| District funded programmes | 261.0 | 174.0 | 255.0 | 154.0 | 239.0 | 189.0 |
| Provincial funded programmes | 219.0 | 124.0 | 210.0 | 110.0 | 278.0 | 112.0 |
| SLBAP programmes | 10.0 | 0.89 | 41.0 | 39.0 | 39.0 | 14.0 |

Table 13: CCB District fund Utilization and SLBAP fund utilization (Rs in million)

| Development programme | 2005-06 |  | 2006-07 |  |  | 2007-08 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Allocated | Utilized | Allocated |  | Utilized | Allocated | Utilized |
| Citizen Community Boards In Khushab-CCB Projects | 130.90 | 14.70 | 142.00 | 9.37 |  | 158.4 | 12.18 |
| SLBAP programmes | 10.0 | 0.89 | 41.0 |  | 39.0 | 39.0 | 14.0 |

The conclusions drawn from the empirical study of the development fund allocation, utilization suggests the degree of interest and willingness attributed by the executing LG agencies in performance of their duties. As of table 15, it is obvious from data of the financial years from 2005-06 to 2007-08 in District Khushab that highest priority was assigned to ADP of the district, followed with provincial funded schemes and least priority was initially given to SLBAP programme. The reasons and factors responsible for this could well be stated as under:

- No accountability for non performance

- Lack of awareness and information of communities

- Lack of incentives for LG staff

- Lack of political will from UC to district level

- Issues of ownership

- LG enabling mechanism of community participation new

- Lack of education at rural community level

Data in Table 16 also presents and endorses the issue of programme ownership and lack of capacity of communities, LG staff to participate in development. Another factor of importance could well be attributed as economic condition of the rural communities as poor small farm owners and tenants may not be able to contribute share of 20% towards the cost. The very fact is also endorsed as recently the ADB authorities have slashed the condition of share of community towards project cost. This has been made effective from current financial year and the figures of development funding utilization also endorse that now a large number of community organizations have come forward with their demands and project performance has improved significantly.

5.2 Ideas and Possibilities

Overall in the ten Project district, communities had positive perception about collective action (CA). Table 17 below is a survey of the three selected project districts to differentiate and indicate similarities and differences in perception in Urban and Rural HHs/Communities.

Table 14: Rural-Urban perceptions on CA/CP in Development (HH survey)

|  | Khushab |  | Mianwali |  | Bhakkar |  |
| --- | --- | --- | --- | --- | --- | --- |
| Description | Rural % | Urban % | Rural % | Urban % | Rural % | Urban % |
| Govt,initiatives do not work and last, until people participate Agree Disagree | 91 9 | 81 19 | 89 11 | 85 15 | 92 8 | 87 13 |
| People need outside help to mobilize Agree Disagree | 62 38 | 25 75 | 51 49 | 19 81 | 65 35 | 17 83 |
| Communities do not have capacity to improve themselves Agree Disagree | 72 28 | 41 59 | 97 3 | 100 0 | 84 16 | 87 13 |
| Government should act upon community driven and demanded initiative Agree Disagree | 98 2 | 89 11 | 93 7 | 96 4 | 92 8 | 87 13 |

The data presents a situation where rural communities are seemingly much more aware of the benefits of CA and most probable reason for this awareness is the decentralization reforms which have been designed as a vehicle for local economic development through community participation by utilizing local resources and regenerating opportunities available. Rural communities do realize that they need capacity building for CA initiatives but also agree that they can help themselves.

5.3 Political Leadership

Rural communities assign much importance to political leadership as compared to urban people, both at the community organization level, but also see it vital at LG institutional level for getting access to information and resources as the project benefits come through LG institutions.

Table 15: Rural-Urban perceptions on leadership in Development (HH survey)

|  | Khushab |  | Mianwali |  | Bhakkar |  |
| --- | --- | --- | --- | --- | --- | --- |
| Description | Rural % | Urban % | Rural % | Urban % | Rural % | Urban % |
| Do you consider leadership an important factor for CA and its success? Agree Disagree | 97 3 | 89 11 | 89 11 | 75 15 | 92 8 | 88 12 |
| Do you consider politics as instrumental in choices and giving favours? Agree Disagree | 100 00 | 75 25 | 98 2 | 90 10 | 90 10 | 81 19 |
| Is your leadership responsive? Agree Disagree | 72 28 | 41 59 | 90 10 | 70 30 | 79 21 | 50 50 |
| Do you consider leadership should be accountable? Agree Disagree | 90 10 | 89 11 | 91 9 | 95 5 | 88 12 | 87 13 |

There is a strong agreement on the role of leadership and a greater emphasis on political factor as playing a role for giving favoritism to the voters and supporters and marginalizing those from the opposition party. It is pertinent to mention here that this survey was carried out in the communities outside of the project areas but included in the districts and they believed that they had been excluded from the project due to political considerations and choices by their district leadership.

5.4 Access to Information

Since the formation of LGs in the country there has been much information dissemination about community driven and enabling government initiatives in the form of CCB programme of the DGs. However, it has been observed since the devolution reforms that only a few influential and thus informed members of the rural communities were able to access these resources. Most of the CCB funding was directed in the districts towards big farmers, worthy members and supporters of the DG leadership and a large number of people i.e. poorest of the poor were still marginalized, primarily due to lack of information and access issues. A survey carried out (Table 18) in the three selected districts in two selected communities (one each from project and non project areas) reveals that not only there is lack of access to information but that information was stifled from them being from the opponent political affiliated parties.

Table 16: composite index of significant differences in information sharing (HH survey)

| Q: Are you aware of the SLBAP & CCB programmes and its economic benefits? | Sufficient information shared (%) | Insufficient information shared (%) |
| --- | --- | --- |
| KHUSHAB Uchali Jalalpur | 76 22 | 24 78 |
| MIANWALI Chapri Isa Khel | 81 11 | 19 91 |
| BHAKKAR Mankera Okhli Mohla | 85 23 | 15 77 |

5.5 Lack of Accountability Mechanisms in DG

It was my personal experience of having served in one of the project districts in the DG set up as District Project Coordinator for SLBAP in 2005-07 that I realized the inherent shortcoming of the project framework which lacked a mechanism of accountability for the official of LGs who often ignored their duty assigned for support and facilitation to communities. In many of the District Development Committees (DDC) meetings this aspect was highlighted with suggestions of devising such a mechanism as well as providing incentives to the staff for the work and contribution towards SLBAP.

The District Coordination Officer DCO is the principal accounting officer of the district and responsible for financial discipline and management of accounts of the entire development and non development funds of a district. In case of audit objections, he is held responsible and answerable for any discrepancies and accountable before the district assembly as well. In my discussions which I held with all the ten DCOs of the district with explicit view about SLBAP project and DG involvement and performance, all of them were in consensus on the issue of “Accountability” for the project funds on the pattern of DG development fund audit and account procedures. They all agreed that project under performance in the start in 2005 was partly due to this very reason when not a single scheme could kick off in all the ten districts. It was later endorsed from the facts when the provincial government help was sought by ADB and SLBAP project funds was made part of the DG one line annual grant and auditor general was assigned annual audit of the projects in each district.

5.6 Administrative and Financial Support

The project design for implementation provided major role play by LGs. To what extent did it work, has been a question of discussion, both in public sector and CBOs/NGOs in project area particularly. Besides the secondary data, interviews and group discussions with LG officials and members of CBOs/NGOs in three most performing project District suggests interesting results. With reference to administrative support, officials of LGs of all LGs disagreed complaining about low salaries, bad working conditions and absence of incentives particularly living in remote rural areas with limited facilities for health and education. Most of the respondents from LG and CBOs as well, respondents mentioned political constellations and choices made on political basis. With regard to financial support mechanisms, both LG officials and representatives from CBOs and NGOs indicated smooth flow of funds from PMU to LG and onwards to projects.

Table 17: Survey of Administrative and Financial support to SLBAP from LGs

|  | Khushab |  | Mianwali |  | Bhakkar |  |
| --- | --- | --- | --- | --- | --- | --- |
| Description | LG officials % | CBOs/NGOs % | LG officials % | CBOs/NGOs % | LG officials % | CBOs/NGOs % |
| LGs recognize/involve CBOs/NGOs in planning process. Agree Disagree | 95 5 | 20 80 | 93 07 | 15 85 | 97 3 | 24 76 |
| Sufficient funds are available with LGs for community based programmes. Agree Disagree | 85 15 | 55 45 | 71 29 | 44 66 | 65 35 | 57 43 |
| LGs arrange incentives for its staff such as salaries, promotions, incentives and training etc. Agree Disagree | 22 28 | 41 59 | 21 3 | 100 0 | 24 16 | 87 13 |
| Project design supports LG role Agree Disagree | 98 2 | 89 11 | 93 7 | 96 4 | 92 8 | 87 13 |

5.7 Political Constellations in Community Based Development

Political support for SLBAP has been a matter of concern particularly at the beginning of project. This has primarily been owing to reason that project design provided for role of union level political leaders who are responsible for initial stage approval of CBO for forwarding proposal to LGs. Experiences from the field showed choice and discretion exercised in approval at union level. This aspect was explored by in-depth interviews of CBO members in project areas as well as from non project areas, who complained political victimization.

Out of five (5) randomly selected CBOs from project and non project areas, which have not benefitted from the project when interviewed with this specific question, almost all came with the answer that political choice did play a role in availing project benefits.

5.8 Synthesizing Best Practices of Participatory Governance

Effective and meaningful participation by the community for CA and local economic development is important for community development. The LG institutional system of governance at the local and grass roots level is the vehicle for this purpose. The enabling spaces for community participation embedded in the system provide opportunity for their role play and now it is up to the people how effectively they can manage to participate in their own development and economic benefit, thereby bringing themselves out of poverty and earning livelihoods for themselves. With the initial structures in lace, it is up to the community to benefit from the scarce resources. A synthesis of some of the crucial elements of PG, CP and CM into a formal and systemized method is imperative for moving ahead:

- De politicization of development

- Accountable leadership

- Community mobilization

- Access to information for all

- Belief in people perception about CA

- Institutionalised form of sanction

- Participation of women

- Capacity building of LG and CBOs

- Improved education and literacy level

It needs an effort to realize all the above owing to the unpredictable human behavior and the fact that it needs a holistic approach to surmount this challenge to transform the testing approaches into prescribed procedures and institutionalized actions.

5.9 Conclusion

When this research began, it was reasonable to think that actors such as LG, P.S, NGOs, CBOs and donors may have been acting in a way contrary to what was designed in the project implementation. After all some preliminary data had also suggested various actors behaving in a different style. The data presented and analyzed suggests that the SLBAP project, after its initial slow pace has come about to mitigate the adverse effects of the newly experimented coordination of involving LG system in the execution and procedural implementation of the initiatives for poverty reduction in the rain fed areas of barani districts of Punjab province of Pakistan. It also highlights the fact that PG, CP and CM can not and should not be taken for granted in any programme which envisages them.

After some interviews it became clear that following capacity building measures and project briefings, LG institutional set up as well as other actors started to respond in a desirable way. It would not be just to assume that assessments made here represent the interest of the entire community. This is because not all can express their feelings and impressions with equal force and it too may not be the voice of the entire community. Making effective use of the created structures of CP, PG and CM is primarily the responsibility of leadership and without the help of local consensus, serious development of communities will be unable to move beyond inertia to creative action. De politicizing development is imperative for providing and distributing equal opportunities and benefits of development interventions. On top of this the leadership has the additional duty of building communities, Bringing members of the community together irrespective of their socio economic, political or ethnic identity for shared goals. This is what sustainable development is all about as defined and promised in Participatory Governance.

Moreover it became clearer through observations and informal interviews that attitudes of actors did not promote spaces for participation. LG attention was too focused on its own development agenda leaving little room for SLBAP project support.

Finally, project design approach to invite CBOs for project proposals through political office holders at ward level propagates choices and thus seen a de merit which alone made project selection and identification difficult for the most needy, poor and marginalized community which was to be targeted. Since then project design has been reviewed and changes have been made to undo the negative impact of de politicization of the initiative.

BIBLIOGRAPHY

Andrew & goldsmith M (1998) From Local Government to Local Governance and beyond? International Political Science Review 19(2):101-117

Annual Progress Report, (2005-6) Sustainable Livelihoods in Barani (Rain Fed) areas project (SLBAP)

Annual Progress Report, (2006-7) Sustainable Livelihoods in Barani (Rain Fed) areas project (SLBAP)

Awortwi, N (2004) Getting the Fundamentals Wrong: Woes of Partnership in Solid waste Collection in Ghanian Cities: Public Administration and Development,24(3):(213-224)

Bamberger, M. (1988) The Role Of Community Participation In Development Planning And Project Management (EDI Policy Seminar Report 13), EDI World Bank; Washington

Bawalya, M.C. (1985) The Integrated Development Approach With The Context Of Decentralization In Zambia. Challenging Rural Poverty Page 183-186 Trenton; Africa World Press

Chambers, R (1983) Rural Development: Putting the Last First; London, Longman

Chohan, A.Y,(2007) Citizen Community Boards(CCB) for Local Development in Punjab-Pakistan,43rd ISOCARP 2007: 1-17

Community Empowerment under Devolution (2006), National Reconstruction Bureau (NRB), Government of Pakistan Report 2006

Cornwall, A (2002) Locating Citizen Participation. IDS Bulletin 33(2): 49-58

Cornwall, A (2002) Locating Citizen Participation. IDS Bulletin 33(2) : 49-58

Data Bank, Pakistan Institute of Development Economics (P.I.D.E), government of Pakistan

Dudley, E (1993) The Critical Villager; Beyond Community Participation. London and New York: Routledge

Esman M.J. & N.T.Uphoff (1998) Local Organizations; Intermediaries in Rural evelopment. Ithaca and London: Cornell University Press

Foster, M (1982) Community Development And Primary Health Care: Their Conceptual Similarities. Journal of the society for applied anthropology; volume 48. No.3:206-216

Gaventa.J, (2002) Explaining Citizen Participation. IDS Bulletin 33(2) : 1-11

Gittel, M (1980) Limits to Citizen Participation; Decline of the Community Organizations. London: Sage Publications; Inc.

Ghazal, M (2004) Community Based and Driven Development-A Critical Review: The World Research Observer

Guimaraes, J.P.C (1992) Participatory Approaches to Rural Development and Rural Poverty Alleviation. Esp. Section 2.3&4

Helmsing A H J,(2002) Decentralization, enablement and local governance in low-   income countries, Institute of Social Studies, The Hague, The Netherlands : 317-340

Helmsing AHJ (Bert) (2002) Decentralization, Enablement and Local Governance in Low Income Countries, Environment and Planning C: Government and Policy 20:317-340

Karishna, A (2003), Partnerships between Local Governments and Community Based Organizations: Exploring the Scope for Synergy: Public Administration and Development: 23(4):361-371

Moser, C.O.N (1986) Community Participation in Urban Development Projects in the “Third World” Progress in Planning (volume 32, part2:81)

Oakely, P. (1991) Bottom Up Versus Top Down: Extension at the Cross Roads, Ceres Jan-Feb 145

Peterse, E.A, & A.M. Simone (1994) Governance and Development; A Critical Analysis Of Community Based Organizations In Western Cape. Foundation for Contemporary Research

Quarterly Progress Report, (2008), Sustainable Livelihoods in Barani (Rain Fed) areas project (SLBAP), Punjab Economic Report, 2007

Shahid A, Z Hussain, A Sarwer, R Majeed, M Saleem Drought Mitigation In Pakistan: Current Status And Options For Future Strategies WP Series (3) International Water Management Institute (IWMI), 2004 Colombo, Sri Lanka.

Smith, B.C. (1998) Participation without with out power: Subterfuge or development? Community Development Journal, 33, 3, 197-204

Smith, D, (1990) Community Participation; Some Realities, Community Development Journal Volume 30. No.1: 159-167

Takashi, k (2005), The Case of Citizen Community Boards in Hafizabad and a Japanese Perspective, IER Hitotsubashi University Japan

UNCHS (HABITAT) (1994) The Community Construction Contract System in Sri Lanka. UNCHS: Nairobi

Valsan (1970) Community Development Programmes and Rural Local Governments: Comparative Case Studies Of India And The Philippines. New York: Praeger Publishers

Wils, F. & B. Helmsing (1996) UNCHS/HABITATs Community Development Programme; Research on the Evolution, Application and Practical Effectiveness Of The CDPs Conceptual Framework (Research Guidelines, Phase 2): The Hague. ISSAS

Wils, F & H. Rijn (1998) Literature Study On Community Participation And Community Management. The Hague: ISSAS

WP 130, Sustainable Livelihood Approach and Programme Development in Cambodia. www.odi.org.uk

APPENDEXES

- Questionnaire for Local Government Officials

- Questionnaire for NGOs/CBOs

Questionnaire for Local Government Officials

Name Of The Local Government …………………………………………………………………………..

Name Of The Department ………………………………………………………………………………….

Please fill in the information you feel appropriate answer to the question (wherever applicable). Please use (Tick) symbol and words/numbers where necessary. Do not fill in questions if you do not know answers.

Respondents Personal Data

- What is the age, sex and education level of the respondent?

- Age........................

- Sex........................

- Education..................................................

- What is the degree of autonomy of the LG in local decision making on policy issues?

- Sufficient autonomy on decision making..............

- Major decisions need approval from CG...............

- CG makes decisions..............................................

- Others 9please specify0........................................................................................

- Who sets the local priority for policy making?

- LG alone................................

- LG policies are influenced by donors/CG.....................

- LG and communities...........................

- Others 9please specify0........................................................................................

- What are the academic and professional qualifications of the Nazim?

- Secondary education..............................

- Tertiary education..................................

- Professional education..............................

- How would you perceive your Nazim of the LG?

- Charismatic.........................

- Visionary...............................

- Innovator...................................

- Strong leader shaker..........................

- Weak leader.................................

- The Nazim has capacity to lead and be followed by the local assembly members?

- Strongly agree......................................

- Agree................................................

- Do not agree......................................

- Strongly disagree..................................

- Others 9please specify).......................................................................

- Does LG formally recognize CBOs as actors in its planning process?

- Yes...........

- No............

- In what areas does the LG involve communities in its activities?

- Setting policy priorities.......................

- Planning of activities...........................

- Community micro plans.........................

- Local budget decisions.............................

- M&E.......................................................

- Do you regularly meet your local communities?

- Yes..........

- No...........

- Do you have any budget provisions in annual budget to co finance community projects?

- Full financing..................

- Co financing......................

- Micro credits.....................

- To what extent is your programme manager effective in performing his/her administrative duties and tactical requirements?

- She/he is effective in operational decisions..............

- She/he allows inputs in decision making............

- Decisions are not transparent....................

- Decision making is top down...........

- Others (please specify)....................................................................................

- Please indicate the type of incentives LG offers to attract/recruit/ retain personnel?

- Good salaries....................

- Promotions.........................

- Training and development.............................

- Working conditions......................................

- Incentives...............................

- Others (please specify)...........................

- Does LG arrange training programmes for staff?

- Strategic planning.........................

- Financial management.............................

- Procurement.............................

- Human resource management..................

- Engineering...............................

- Public works..............................

- Social services..................................

- Participatory approaches to governance........................

- Have you been involved in LG internal decision making?

- Yes..........

- No...........

- Does the LG have any budgetary discretion?

- No. All expenditures need approval from CG...........

- LG is allowed to spend up to a limit.....................

- LG is allowed to spend against allocation and without limit...............

- LG has authority for appropriations......................

- Does the LG have authority to tender its projects and choose its own contractors?

- No. Works are carried out by CG...............

- Tenders/projects need approval from CG..................

- LG is independent in expenditures

- Rate the degree of trustfulness and comprehensiveness of LG information on financial resources?

- Good quality information...................

- Low quality information.....................

- Open budget procedures......................

- SLBAP project policy for implementation provides good mechanisms for LG involvement

- Strongly agree.......................

- Agree....................................

- Disagree.............................

- Others.....................................

- SLBAP project support from PMU has been effective

- Strongly agree.......................

- Agree....................................

- Disagree.............................

- Others.....................................

- Community empowerment by SLBAP has been effective and duly supported

- Strongly agree.......................

- Agree....................................

- Disagree.............................

- Others.....................................

- Political interference and political constellations affect project performance and tend to deprive deserving communities

- Strongly agree.......................

- Agree....................................

- Disagree.............................

- Others.....................................

- To what extent SLBAP assures financial flow of funds timely?

- Always assures.......................

- Response is lukewarm....................

- Never assures.............................

- Others.......................................

- Do you think SLBAP mode of poverty reduction is better than LG own community based initiatives?

- Yes........

- No..........

- Are you satisfied with SLBAP project objectives?

- Yes.........

- No..........

Questionnaire for NGOs/CBOs

Name Of The NGO/CBO …………………………………………………………………………..

Name Of The District ………………………………………………………………………………….

Please fill in the information you feel appropriate answer to the question (wherever applicable). Please use (Tick) symbol and words/numbers where necessary. Do not fill in questions if you do not know answers.

Respondents Personal Data

- What is the age, sex and education level of the respondent?

- Age........................

- Sex........................

- Education..................................................

- What is the degree of compromise between LG and CBOs/NGOs in accomplishing project goals of SLBAP?

- Sufficient autonomy on decision making..............

- Major decisions need approval from LG...............

- LG makes decisions..............................................

- Others 9please specify0........................................................................................

- Who sets the local priority for project identification for communities?

- LG alone................................

- LG and communities...........................

- Others please specify0........................................................................................

- Did you participate as beneficiary for SLBAP funding? If yes, to what extent are you satisfied with goals achieved?

- Yes.........

- No..........

- 100%...........

- 50%..............

- 10%.............

- Others...........

- Did you receive satisfactory support from SLBAP or LG line departments?

- Yes..........

- No...........

- Do you agree that when LG or a donor talks about low income groups participation, it is only for political purposes and not real?

- Strongly agree........

- Agree............

- Disagree..........

- Strongly disagree........

- Projects such as SLBAP should be the basic guidelines for LG support

- Strongly agree........

- Agree............

- Disagree..........

- Strongly disagree........

- Is the support from LG a key to success of SLBAP project?

- Strongly agree........

- Agree............

- Disagree..........

- Strongly disagree........